## Read me
Job picker and measures tracker
From The AI Rollout Plan by Neosaipien, October 2026 edition. For the leadership team, the owner and the two pilot managers.
HOW TO USE IT
1. Job picker: each pilot team lists 10 to 15 tasks it does, scores value and how often from 1 to 5, and answers the three questions. The sheet works out the score and the ceiling. Pick three jobs across two teams, each at level 1 Read or 2 Draft for the pilot.
2. Measures: for each picked job, take a two-week baseline of the five measures before the pilot, by the same method you will use at day 90. Enter both. The sheet says whether each measure got better.
3. Time saved: note it, with where the time went. It is not the result on its own.
4. Tools register: a short version of the register, one row per AI tool in use, paid or not.
5. Platforms: what Claude, ChatGPT and Gemini are each best at, and which model when, as of Oct 2026. The plan's author recommends Claude first, ChatGPT second, Gemini third; the tool your organisation approves for company data comes first.
The yellow rows are examples, made up to show how the parts work. They name no real organisation or person. Overwrite them or delete them.
VALUE, 1 TO 5
1 Little difference to anyone
2 Saves a person some effort
3 Noticeably faster or better for the team
4 Noticeably better for customers or for money
5 Changes how the team works
HOW OFTEN, 1 TO 5
1 A few times a year
2 Monthly
3 Weekly
4 Daily
5 Many times a day
THE THREE QUESTIONS SET THE CEILING
Can it be undone easily? If not: level 3 at most.
Does it leave the team? A customer, a supplier, the public or money. If so: level 3 at most, and a person presses send.
Does it read outside content? The web, outside email, files others sent. If so: it may not also send, pay or delete without asking.
Take the lowest level any of them allows. Leave out of the first 90 days any job that decides something about a person: hiring, promotion, pay, discipline, task allocation or performance. Those carry their own rules (see Rules for leaders).
THE FOUR LEVELS
1 Read. It looks and reports. It changes nothing.
2 Draft. It drafts. Only a person sends or shares.
3 Ask first. It acts, and asks before each send, pay, delete or change.
4 Alone. It acts inside fixed limits. A person reviews after.
Up one level after five clean runs. Down at once after a surprise.
THE TOOL CHOOSER
Chat: One answer, draft or idea that you use yourself.
Deep research: A cited report on a question, where checking the sources is the work.
Agent: Work whose next step depends on what it finds along the way.
Automation: The same fixed steps every time, written down in advance.
THE RULE
Score = value x how often. Shortlist the highest scores, then take the lowest level the three questions allow. Pick three jobs across two teams, each at level 1 or 2 for the pilot.
Every time in this pack is an estimate. Your own will differ. Free from Neosaipien under the free licence, Version 2, in the LICENCE.txt file that comes with it. Use it as much as you like and change it to fit your team. Hand your changed version to people inside your own organisation, team, class or group, keeping the credit and the date and saying it was changed. Share unchanged copies with anyone, free of charge. Do not sell it, and do not publish a changed version outside your own group.

## Job picker
Job picker
Score each task, answer the three questions, then pick three jobs across two teams for the pilot. Yellow rows are made-up examples.
# | Task | Team | Who does it now | Value (1 to 5) | How often (1 to 5) | Score | Can it be undone easily? | Does it leave the team? | Does it read outside content? | Does it decide something about a person? | Ceiling | Tool | Pilot level | Pick | Owner | Why, or notes | Example?
1 | First drafts of replies to routine customer questions | Customer service |  | 4 | 5 |  | No | Yes | Yes | No |  | Agent | 2 Draft | Yes |  | Highest score. Drafts only: a person reads and sends every reply. | EXAMPLE, MADE UP
2 | Proposal first drafts from our template and past proposals | Sales |  | 5 | 3 |  | No | Yes | No | No |  | Chat | 2 Draft | Yes |  | High value. The sales lead checks the facts and the figures before anything leaves. | EXAMPLE, MADE UP
3 | Weekly summary of themes in customer feedback | Customer service |  | 3 | 3 |  | Yes | No | Yes | No |  | Agent | 1 Read | Yes |  | Reads and reports only. Uses the same team as job 1, so one review covers both. | EXAMPLE, MADE UP
4 | Monthly management report from three systems | Finance |  | 4 | 2 |  | Yes | No | No | No |  | Automation |  | Later |  | The steps are the same every month, so it is an automation project, not a pilot job. | EXAMPLE, MADE UP
5 | Check expense claims against the policy | Finance |  | 3 | 3 |  | Yes | No | No | No |  | Automation |  | Later |  | Fixed checks suit automation; a person decides every exception. | EXAMPLE, MADE UP
6 | Weekly look at competitors' public pages | Marketing |  | 2 | 3 |  | Yes | No | Yes | No |  | Agent |  | No |  | Low value for now. | EXAMPLE, MADE UP
7 | Research a new supplier market and shortlist | Operations |  | 3 | 1 |  | Yes | No | Yes | No |  | Deep research |  | No |  | Too rare to measure in 90 days. | EXAMPLE, MADE UP
8 | Screen job applications | HR |  | 4 | 3 |  | No | Yes | Yes | Yes |  |  |  | Never in the pilot |  | It decides something about a person. See Rules for leaders. | EXAMPLE, MADE UP
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Measures
Measures tracker
Five measures for each picked job: a two-week baseline before the pilot, then day 90, by the same method. Yellow rows are made-up examples.
Job | Team | Measure | How we measure it | Baseline from | Baseline to | Baseline | Day 90 | Change | Better is | Reads as | Scored by | Notes | Example?
First drafts of replies to routine customer questions | Customer service | Quality | Rubric of five points, 1 to 5, 20 replies a week, scored by the team lead |  |  | 3.6 | 3.8 |  | Higher |  |  |  | EXAMPLE, MADE UP
First drafts of replies to routine customer questions | Customer service | Rework | Second replies needed because the first was wrong, per 100 replies |  |  | 7 | 5 |  | Lower |  |  |  | EXAMPLE, MADE UP
First drafts of replies to routine customer questions | Customer service | Turnaround | Median working hours from question to reply, from the inbox timestamps |  |  | 6.5 | 3 |  | Lower |  |  |  | EXAMPLE, MADE UP
First drafts of replies to routine customer questions | Customer service | Errors caught | Errors found at the check before sending, per 100 replies, logged by type |  |  | 2 | 6 |  | Higher |  |  | The check is working; look at what it catches. | EXAMPLE, MADE UP
First drafts of replies to routine customer questions | Customer service | Staff confidence | One question, 1 to 5: “I know what to check before I send an AI draft.” |  |  | 2.9 | 3.7 |  | Higher |  |  |  | EXAMPLE, MADE UP
Proposal first drafts from our template and past proposals | Sales | Quality | Score a sample against one short rubric of three to five points, the same rubric before and after. | [5 empty] | Higher |  |  |  | EXAMPLE, MADE UP
Proposal first drafts from our template and past proposals | Sales | Rework | Count the pieces that had to be redone or corrected after they left the team. | [5 empty] | Lower |  |  |  | EXAMPLE, MADE UP
Proposal first drafts from our template and past proposals | Sales | Turnaround | Take the median time for the same kind of task. | [5 empty] | Lower |  |  |  | EXAMPLE, MADE UP
Proposal first drafts from our template and past proposals | Sales | Errors caught | Log each error found at the check, with what it was. | [5 empty] | Higher |  |  |  | EXAMPLE, MADE UP
Proposal first drafts from our template and past proposals | Sales | Staff confidence | Ask one question, the same each time, scored 1 to 5. | [5 empty] | Higher |  |  |  | EXAMPLE, MADE UP
Weekly summary of themes in customer feedback | Customer service | Quality | Score a sample against one short rubric of three to five points, the same rubric before and after. | [5 empty] | Higher |  |  |  | EXAMPLE, MADE UP
Weekly summary of themes in customer feedback | Customer service | Rework | Count the pieces that had to be redone or corrected after they left the team. | [5 empty] | Lower |  |  |  | EXAMPLE, MADE UP
Weekly summary of themes in customer feedback | Customer service | Turnaround | Take the median time for the same kind of task. | [5 empty] | Lower |  |  |  | EXAMPLE, MADE UP
Weekly summary of themes in customer feedback | Customer service | Errors caught | Log each error found at the check, with what it was. | [5 empty] | Higher |  |  |  | EXAMPLE, MADE UP
Weekly summary of themes in customer feedback | Customer service | Staff confidence | Ask one question, the same each time, scored 1 to 5. | [5 empty] | Higher |  |  |  | EXAMPLE, MADE UP

## Time saved
Time saved
A note, not the result. Write down where the time went, and whether that is what the leadership team decided.
Week | Job | Team | Hours saved (an estimate) | Where the time went | What we decided it was for | Same? | Example?
Week 6 | First drafts of replies to routine customer questions | Customer service | 6 | Faster replies; two people cleared the backlog of open questions | Faster replies to customers | Yes | EXAMPLE, MADE UP

## Tools register
Tools and connections register (short)
One row per AI tool anyone uses for work, paid or not. Record what is true today. The Team AI Policy Kit has the full register with guidance.
Tool and plan | Who may use it | Data allowed | Connected apps | Can they write? | Approval setting | Memory | Scheduled tasks | Owner | Review date | Example?
[Assistant], business plan | All staff | Internal, no personal data | Shared drive | Read only | Ask first | Off | None | [owner] | [date] | EXAMPLE, MADE UP
Note-taker inside [video app] | Found in use by 4 people | Not yet decided | Calendar | Yes | Not known | Not known | Every meeting | None yet | [date] | EXAMPLE, MADE UP

## Platforms
Which platform for which job
The plan's author recommends claude first, ChatGPT second, Gemini third. For company data, use the tool your organisation approves. A personal preference never beats the company's data rules. As of Oct 2026, read on each vendor's own pages on 16 Oct 2026.
Task | Claude is best at | ChatGPT is best at | Gemini is best at | For most office workers
Writing | Clear business writing (Anthropic's claim for Opus 5.5); Claude Docs on every plan | Fast drafts in Chat; ChatGPT for Word even on Free | Writing inside Gmail and Docs at Google companies | Claude
Documents | Finished Word, PDF or Google Docs from one conversation; Claude for Word | Reports and Pages from Work | Gemini in Docs for Workspace users | Claude
Spreadsheets | Claude for Excel: cell references, formula-safe edits, overwrite warnings | Excel and Google Sheets add-ins; the Data plugin | Gemini in Sheets for Workspace users | Claude
Slides | Claude Slides on every plan; Claude for PowerPoint | Following company templates (OpenAI's claim for Astra); PowerPoint add-in | Gemini in Slides | Claude, with ChatGPT close
Research | Research that mixes the web with your connected work tools | Most control: edit the plan, limit it to named sites | Free Deep Research; Gemini Notebook for your own sources | ChatGPT for control over sources; Gemini Notebook for your own files
Routines and software | Claude Code; scheduled tasks and Dispatch for office routines | Codex; tasks that start on a new email, Slack message or pull request | Antigravity; schedules in tasks (personal accounts) | Claude for building; ChatGPT for routines that start on an event
Meetings | Working from a transcript you give it | Meetings plugin (beta, Mac) and audio uploads | Take notes for me in Google Meet | Gemini if you meet in Google Meet, otherwise ChatGPT
Email | Gmail connector; Claude for Outlook | Gmail and Outlook Email apps; tasks that start on a new Gmail message | Gemini built into Gmail | Gemini inside Gmail; Claude or ChatGPT for Outlook
Images | Designs, mockups and diagrams (Claude Design) | ChatGPT Images 2.5 | Nano Banana images; Gemini Omni video | ChatGPT or Gemini
WHICH MODEL WHEN
The job | Claude | ChatGPT | Gemini
Quick question, short rewrite, sort a list | Haiku 5.5 or Sonnet 5.5 | GPT-6 at Instant | Auto or Flash-Lite
Everyday writing, a summary, a first deck | Sonnet 5.5 at its Default effort | GPT-6 at Medium | Flash
A careful report, a messy spreadsheet | Opus 5.5 | GPT-6 at High | Pro, thinking High
Hand over a multi-step task | Opus 5.5, in an ordinary conversation | Work with Default, or GPT-6.1 Sol | Task with Flash or Argon
The hardest, high-stakes work | Fable 5.1 (it uses limits fastest) | GPT-6 at Pro, or GPT-6 Astra in Work | Argon, thinking High
Start with the default. Move up only when the answer misses something that matters. Not every model is on every plan. Neosaipien is not affiliated with Anthropic, OpenAI or Google.

## Lists
Yes or no | Tool | Pilot level | Pick | Level | Measure | Better is
Yes | Chat | 1 Read | Yes | 1 Read | Quality | Higher
No | Deep research | 2 Draft | Later | 2 Draft | Rework | Lower
| Agent |  | No | 3 Ask first | Turnaround
| Automation |  | Never in the pilot | 4 Alone | Errors caught
Staff confidence