## Slide 1
Our AI rollout: the next 90 days
[Organisation name]. What we decide today, what changes for our people, and how we will know it worked.
[Presenter name], [date]
From The AI Rollout Plan by Neosaipien, October 2026 edition.
Notes: Thank you for the time. We have bought AI tools and some people use them well, but nothing yet says what they are for here, what the rules are, or whether anything got better. This meeting is to agree those three things and the first 90 days. I will take about 25 minutes, and I want the rest for decisions. At the end we will have an owner, two pilot teams, the rules we adopt and the date of the next review.

## Slide 2
The tools are the easy part
Organisation over individual
Organisational factors account for “more than 2x the reported AI impact of individual factors” (67% vs 32%). An association, not a cause.
Microsoft, Work Trend Index, 5 May 2026: 20,000 AI users, 10 countries
Leaders out of step
Only 26% of AI users say their leadership is “clearly and consistently aligned on AI”.
Same survey
Redesign over add-ons
Nearly three-quarters of McKinsey's “AI high performers” have fundamentally redesigned workflows.
McKinsey survey of 1,719 people, reported by Fortune, 2 Sep 2026
Microsoft and McKinsey sell AI services, and these surveys are self-reported.
Notes: Three findings from this year. First, Microsoft's survey of 20,000 people who use AI at work found that the organisation around a person matters about twice as much as the person's own habits, for the impact they report. It is an association, not proof of cause. Second, only about a quarter say their leaders are aligned on AI. Third, a McKinsey survey found that nearly three-quarters of the firms getting the most from AI have fundamentally redesigned how the work is done. Both firms sell AI services and these are self-reported surveys, so treat them as direction, not precision. The point for us: buying more tools will not do it. What we decide in this room will.

## Slide 3
What we have, and what we don't
Tools we pay for
[list, from the register]
People using them
[number or share, if known]
Written rules
[none / draft / adopted on date]
Who owns it
[nobody yet / name]
How we measure it
[nothing yet / what we measure]
Notes: This is our starting point, in plain numbers. Fill it from the tools and connections register before the meeting. If a row says nobody or nothing, say so: that is the reason for this plan, not a failure of anyone in the room.

## Slide 4
What only this room can do
Decide
What AI is for here, which three jobs go first, who owns it.
Set the rules
What never goes in, who checks, what AI may do alone.
Use it yourself
One real task a week, briefed and checked, shown to your team.
A Microsoft-led study of 1,800 workers (Jul 2025): when managers actively modelled AI use, employees reported a 17-point lift in reported AI value. Self-reported.
Notes: These three jobs cannot be delegated to IT or to the keen few. Decide: what it is for and what goes first. Set the rules: the policy, what never goes in, who checks. And use it yourself. In a Microsoft-led study of 1,800 workers, employees whose managers used AI in the open reported a 17-point lift in the value they got from it. That is self-reported, but it matches what we would expect: people copy what their manager does, not what the policy says.

## Slide 5
One main platform, then a second for named jobs
Claude
One conversation for questions and tasks. Asks before acting by default. Docs, Slides and Claude for Excel.
ChatGPT
Work for tasks that end in a file. Routines that start when an email arrives. Pictures.
Gemini
Inside Gmail, Docs, Sheets and Meet at Google companies. Its Task agent is for personal accounts, for now.
The plan's author recommends Claude first, ChatGPT second, Gemini third. The tool we already approve for company data comes first. As of Oct 2026.
Notes: Three platforms now do most of what our people need: Claude, ChatGPT and Gemini. Each wins somewhere: Claude for one simple place to ask and hand over work, with finished documents and spreadsheets; ChatGPT for routines that start when an email arrives, and for pictures; Gemini inside Google's own apps. The plan's author recommends Claude first, ChatGPT second, Gemini third, and pages 6 to 8 give the reasons. But if we already approve one tool for company data, that one comes first. Today we agree our main platform, and we add a second only when a named job needs it.

## Slide 6
Decide, pilot, then scale, fix or stop
Decide and set the rules
Owner, alignment, register, policy, three jobs, baseline, questions to IT
Pilot
Two teams, two workshops, levels 1 and 2 only, a weekly 20-minute review
Scale, fix or stop
A decision for each job from its numbers, skills, the training record, a report to the board
Notes: Three stages. In the first 30 days we decide and set the rules, and we measure before anything changes. In the next 30, two teams try three jobs, where AI only reads and reports, or drafts for a person to send. They review every week for 20 minutes. In the last 30 we decide each job on its numbers: scale it, fix it, or stop it. Stopping a job that does not work is a good result, not a failure.

## Slide 7
Three jobs, two teams, levels 1 and 2
[Job 1]
[Team]
[Level 1 Read or 2 Draft]
[Job 2]
[Team]
[Level]
[Job 3]
[Team]
[Level]
Chosen with the job picker: value, how often, and three questions. Can it be undone easily? Does it leave the team? Does it read outside content?
Notes: These are the candidates from the job picker. Each scored high on value and on how often it happens, and each passes the three questions at level 1 or 2: it reads and reports, or it drafts and a person sends. Nothing in the pilot decides anything about a person, such as hiring or performance; those carry their own rules, and this deck is not legal advice on them, so we check them with our own adviser. Today we confirm the three, or swap one.

## Slide 8
Time saved is not value
Quality
Rework
Turnaround
Errors caught
Staff confidence
Measured for each job, by the same method, for two weeks before the pilot and again at day 90.
Time saved becomes value only when we decide what it is for, team by team.
Notes: We will measure five things for each job, starting with a two-week baseline before the pilot: quality, rework, turnaround, errors caught at the check, and staff confidence. We will note time saved, but time saved only becomes value if we decide what it is for. So we decide that today, team by team.

## Slide 9
Six things to agree before we leave
Owner
[name], with [hours] a week for 90 days
Main platform
[platform], and a second only for [named jobs]
Pilot teams
[team] and [team]
The rules
Adopt the policy by [date]
Time saved
Goes to [what], team by team
Next review
[date], then monthly
Notes: Six decisions, and we write them on the worksheet now: the owner and their time, our main AI platform, the two pilot teams, the date we adopt the policy, what the time saved goes to, and the date of the next review. If we cannot agree one of these today, we name who decides it and by when.