## Slide 1
Our AI rollout: the plan on a page
Decide and set the rules, pilot with two teams, then scale, fix or stop each job on its numbers.
Organisation [name]
Owner [name]
Day 1 [date]
What AI is for, the platform, three jobs, an owner
What never goes in, who checks, ask first
One real task a week, shown to the team
Decide and set the rules
Name an owner
The leader
Hold a leadership alignment session
The leadership team
Fill in the tools and connections register
The owner, with IT or the admin
Adopt the policy
The leadership team
Choose three first jobs with the job picker
The owner and two team managers
Take baseline measures
The two team managers
Put the questions to IT or the admin
The owner
Leaders agree what AI is for, the rules are out, three first jobs are chosen and measured before anything changes.
Pilot
Start with two teams
The owner
Run the two workshops
Each pilot team
Levels 1 and 2 only
Each pilot team
Hold a weekly 20-minute review
Each pilot team and the owner
Decide what to do with the time saved
The leadership team
Managers model it
Every leader and pilot manager
Two teams do the three jobs at levels 1 and 2, review them every week, and their managers use AI in the open.
Scale, fix or stop
Make a decision for each job
The leadership team
Write the team's way of doing a task as a skill
The pilot manager
Move up one level after five clean runs
The pilot manager
Keep the record of AI training
The owner
Report to the board
The leader and the owner
Each job gets a decision from its numbers, the good ones are written down as skills, and the board hears what changed.
The monthly rhythm
A monthly leadership update
The owner
Recheck the register and the settings
The owner, with IT or the admin
One job in, one job decided
The leadership team
Review the policy and the training record
The owner
One meeting a month keeps the jobs, the rules and the tools current.
1 Read. It looks and reports. It changes nothing.
2 Draft. It drafts. Only a person sends or shares.
3 Ask first. It acts, and asks before each send, pay, delete or change.
4 Alone. It acts inside fixed limits. A person reviews after.
Up one level after five clean runs. Down at once after a surprise.
Can it be undone easily? Does it leave the team? Does it read outside content? Any risky answer: level 3 at most.
Never in the first 90 days: a job that decides something about a person.
Quality / Rework / Turnaround / Errors caught / Staff confidence
Time saved is not value. Decide what it is for before it is saved.
From The AI Rollout Plan by Neosaipien, October 2026 edition. Times are estimates. Not legal advice. Neosaipien is not affiliated with Anthropic, OpenAI or Google.
Notes: Edit the brackets, then print on A4 or US Letter, landscape, or share it as the first slide of your monthly update. Every step here has a page in The AI Rollout Plan.